## Revision History
TEAM 01 - ZOOM
SEP - RELEASE PLAN
Project Name: | Website for company project management
Scrum Master: | Le Thi Loi
Mentor: | Phan Thi Hong
Start Date: | 10/03/2022 | End Date: | 02/04/2023
Historical Revisions
Version | Date | Author | Content
1.0 | 21/10/2022 | Le Thi Loi | Create template
1.1 | 03/11/2022 | Nguyen Thanh Thien | Edit content Release Plan
1.2 | 08/11/2022 | Le Thi Loi | Update release

## Release Plan
RELEASE PLAN
RELEASE | SPRINT | FEATURE NAME | CATEGORY | START | END | DURATION (DAY) | STATUS | RELEASE DATE | GOAL
1 | 2 | Login | Feature | 2022-11-14 | 2022-12-04 | 18 | Released | 2022-12-27 | Admin Log in to the website system with the provided account
| 2 | Logout | Feature | 2022-11-14 | 2022-12-04 | 18 | Released |  | Admin Logs out of website system | Planned
| 2 | View Personal Information | Feature | 2022-11-14 | 2022-12-04 | 18 | Released |  | Admin View Personal Information | Ongoing
| 2 | Change Password | Feature | 2022-11-14 | 2022-12-04 | 18 | Released |  | Admin Change Password | Released
| 2 | Forgot Password | Feature | 2022-11-14 | 2022-12-04 | 18 | Released |  | Admin Forgot Password
| 2 | Update personal information | Feature | 2022-11-14 | 2022-12-04 | 18 | Released |  | Admin Update Personal Information
| 2 | View Employee List | Feature | 2022-11-14 | 2022-12-04 | 18 | Released |  | Admin View Employee List
| 2 | Search Employee | Feature | 2022-11-14 | 2022-12-04 | 18 | Released |  | Admin Search Employee
| 2 | View Employee Details | Feature | 2022-11-14 | 2022-12-04 | 18 | Released |  | Admin View Employee Details
| 2 | Add Employee | Feature | 2022-11-14 | 2022-12-04 | 18 | Released |  | Admin Add Employee
| 2 | Update Employee Information | Feature | 2022-11-14 | 2022-12-04 | 18 | Released |  | Admin Update Employee Information
| 2 | View Work Progress | Feature | 2022-11-14 | 2022-12-04 | 18 | Released |  | Admin Work Progress
| 2 | View Projects that employees have participated in | Feature | 2022-11-14 | 2022-12-04 | 18 | Released |  | Admin Projects that employees have participated in
| 2 | View Activity History | Feature | 2022-11-15 | 2022-12-04 | 18 | Released |  | Admin View Activity History
| 2 | View Payroll Sheet | Feature | 2022-11-15 | 2022-12-04 | 18 | Released |  | Admin View Payroll Sheet
| 2 | Lock/Unlock Account | Feature | 2022-11-15 | 2022-12-04 | 18 | Released |  | Admin Account Lock/Unlock
| 2 | View Statistical reports | Feature | 2022-11-15 | 2022-12-04 | 18 | Released |  | Admin Statistical reports
| 2 | View Role List | Feature | 2022-11-14 | 2022-12-04 | 18 | Released |  | Admin View Role List
| 2 | Search Role | Feature | 2022-11-14 | 2022-12-04 | 18 | Released |  | Admin Search Role
| 2 | Add Role | Feature | 2022-11-14 | 2022-12-04 | 18 | Released |  | Admin Add Role
| 2 | Edit Role | Feature | 2022-11-14 | 2022-12-04 | 18 | Released |  | Admin Edit Role
| 2 | Delete Role | Feature | 2022-11-14 | 2022-12-04 | 18 | Released |  | Admin Delete Role
| 3 | View Recruitment News | Feature | 2022-12-05 | 2022-12-25 | 18 | Released |  | Admin View Recruitment News
| 3 | Search Recruitment News | Feature | 2022-12-05 | 2022-12-25 | 18 | Released |  | Admin Search Recruitment News
| 3 | Add Recruitment News | Feature | 2022-12-05 | 2022-12-25 | 18 | Released |  | Admin Add Recruitment News
| 3 | Edit Recruitment News | Feature | 2022-12-05 | 2022-12-25 | 18 | Released |  | Admin Edit Recruitment News |  | S
| 3 | Close/Open Recruitment News | Feature | 2022-12-05 | 2022-12-25 | 18 | Released |  | Admin Close/Open Recruitment News
| 3 | Delete Recruitment News | Feature | 2022-12-05 | 2022-12-25 | 18 | Released |  | Admin Delete Recruitment News
| 3 | View a list of customer consultation information | Feature | 2022-12-05 | 2022-12-25 | 18 | Released |  | Admin View a list of customer consultation information
| 3 | Search consultation information | Feature | 2022-12-05 | 2022-12-25 | 18 | Released |  | Admin Search consultation information
| 3 | Reception - refuse consultation information | Feature | 2022-12-05 | 2022-12-25 | 18 | Released |  | Admin Reception - refuse consultation information
| 3 | Send consulting contact information | Feature | 2022-12-05 | 2022-12-25 | 18 | Released |  | User Send consulting contact information
| 3 | View Recruitment News | Feature | 2022-12-05 | 2022-12-25 | 18 | Released |  | User View Recruitment News
| 3 | Search Recruitment News | Feature | 2022-12-05 | 2022-12-25 | 18 | Released |  | User Search Recruitment News
| 3 | View Recruitment News Details | Feature | 2022-12-05 | 2022-12-25 | 18 | Released |  | User View Recruitment News Details
| 3 | View Home Page | Feature | 2022-12-05 | 2022-12-25 | 18 | Released |  | User View Home Page
| 3 | View Intro | Feature | 2022-12-05 | 2022-12-25 | 18 | Released |  | User View Intro
| 3 | View successful projects | Feature | 2022-12-05 | 2022-12-25 | 18 | Released |  | User View successful projects
| 3 | View questions | Feature | 2022-12-05 | 2022-12-25 | 18 | Released |  | User View questions
2 | 4 | View Task List | Feature | 2022-12-26 | 2022-12-25 | 18 | Ongoing | 2023-02-19 | Admin View Task List
| 4 | Search Task | Feature | 2022-12-26 | 2023-01-15 | 18 | Ongoing |  | Admin Search Task
| 4 | Add Task | Feature | 2022-12-26 | 2023-01-15 | 18 | Ongoing |  | Admin Add Task
| 4 | View Task Details | Feature | 2022-12-26 | 2023-01-15 | 18 | Ongoing |  | Admin View Task Details
| 4 | Edit Task | Feature | 2022-12-26 | 2023-01-15 | 18 | Ongoing |  | Admin Edit Task
| 4 | Delete Task | Feature | 2022-12-26 | 2023-01-15 | 18 | Ongoing |  | Admin Delete Task
| 4 | View Project List | Feature | 2022-12-26 | 2023-01-15 | 18 | Ongoing |  | Admin View Project List
| 4 | Search Project | Feature | 2022-12-26 | 2023-01-15 | 18 | Ongoing |  | Admin Search Project
| 4 | View Project Details | Feature | 2022-12-26 | 2023-01-15 | 18 | Ongoing |  | Admin View Project Details
| 4 | Add Project | Feature | 2022-12-26 | 2023-01-15 | 18 | Ongoing |  | Admin Add Project
| 4 | Edit Project Information | Feature | 2022-12-26 | 2023-01-15 | 18 | Ongoing |  | Admin Edit Project Information
| 4 | Delete Project | Feature | 2022-12-26 | 2023-01-15 | 18 | Ongoing |  | Admin Delete Project
| 4 | View Debts | Feature | 2022-12-26 | 2023-01-15 | 18 | Ongoing |  | Admin View Debts
| 4 | Add Debt | Feature | 2022-12-26 | 2023-01-15 | 18 | Ongoing |  | Admin Add Debt
| 4 | Edit Debt | Feature | 2022-12-26 | 2023-01-15 | 18 | Ongoing |  | Admin Edit Debt
| 4 | Delete Debt | Feature | 2022-12-26 | 2023-01-15 | 18 | Ongoing |  | Admin Delete Debt
| 4 | View list and search as Skills | Feature | 2022-12-27 | 2023-01-16 | 18 | Ongoing |  | Admin View list and search as Skills
| 4 | Add new Skills | Feature | 2022-12-28 | 2023-01-17 | 18 | Ongoing |  | Admin Add new Skills
| 4 | Edit Skills | Feature | 2022-12-29 | 2023-01-18 | 18 | Ongoing |  | Admin Edit Skills
| 4 | Delete Skills | Feature | 2022-12-30 | 2023-01-19 | 18 | Ongoing |  | Admin Delete Skills
| 4 | View list and search as Skills Category | Feature | 2022-12-31 | 2023-01-20 | 18 | Ongoing |  | Admin View list and search as Skills Category
| 4 | Add new Skills Category | Feature | 2023-01-01 | 2023-01-21 | 18 | Ongoing |  | Admin Add new Skills Category
| 4 | Edit Skills Category | Feature | 2023-01-02 | 2023-01-22 | 18 | Ongoing |  | Admin Edit Skills Category
| 4 | Delete Skills Category | Feature | 2023-01-03 | 2023-01-23 | 18 | Ongoing |  | Admin Delete Skills Category
| 4 | View list and search as Subsidies | Feature | 2023-01-04 | 2023-01-24 | 18 | Ongoing |  | Admin View list and search as Subsidies
| 4 | Add new Subsidies | Feature | 2023-01-05 | 2023-01-25 | 18 | Ongoing |  | Admin Add new Subsidies
| 4 | Edit Subsidies | Feature | 2023-01-06 | 2023-01-26 | 18 | Ongoing |  | Admin Edit Subsidies
| 4 | Delete Subsidies | Feature | 2023-01-07 | 2023-01-27 | 18 | Ongoing |  | Admin Delete Subsidies
| 4 | View list and search as Department | Feature | 2023-01-08 | 2023-01-28 | 18 | Ongoing |  | Admin View list and search as Department
| 4 | Add new Department | Feature | 2023-01-09 | 2023-01-29 | 18 | Ongoing |  | Admin Add new Department
| 4 | Edit department | Feature | 2023-01-10 | 2023-01-30 | 18 | Ongoing |  | Admin Edit department
| 4 | Delete Department | Feature | 2023-01-11 | 2023-01-31 | 18 | Ongoing |  | Admin Delete Department
| 5 | View Partner List | Feature | 2023-01-30 | 2023-02-19 | 18 | Ongoing |  | Admin View Partner List
| 5 | Search Partner | Feature | 2023-01-30 | 2023-02-19 | 18 | Ongoing |  | Admin Search Partner
| 5 | View Partner Information Details | Feature | 2023-01-30 | 2023-02-19 | 18 | Ongoing |  | Admin View Partner Information Details
| 5 | Edit Partner Information | Feature | 2023-01-30 | 2023-02-19 | 18 | Ongoing |  | Admin Edit Partner Information
| 5 | Send email | Feature | 2023-01-30 | 2023-02-19 | 18 | Ongoing |  | Admin Send email
3 | 6 | Payroll | Feature | 2023-02-20 | 2023-03-12 | 18 | Planned | 2023-04-02 | Admin Payroll
| 6 | Update Tax Index | Feature | 2023-02-20 | 2023-03-12 | 18 | Planned |  | Admin Update Tax Index
| 6 | View Payroll Sheet | Feature | 2023-02-20 | 2023-03-12 | 18 | Planned |  | Admin View Payroll Sheet
| 6 | View Payroll Details | Feature | 2023-02-20 | 2023-03-12 | 18 | Planned |  | Admin View Payroll Details
| 6 | Export Payroll | Feature | 2023-02-20 | 2023-03-12 | 18 | Planned |  | Admin Export Payroll
| 7 | View Report - Statistics | Feature | 2023-03-13 | 2023-04-02 | 18 | Planned |  | Admin View Report - Statistics
| 7 | Export Report - Statistics | Feature | 2023-03-13 | 2023-04-02 | 18 | Planned |  | Admin Export Report - Statistics
| 7 | Edit contact information, avatar | Feature | 2023-03-13 | 2023-04-02 | 18 | Planned |  | Employee Edit contact information, avatar
| 7 | View Task List | Feature | 2023-03-13 | 2023-04-02 | 18 | Planned |  | Employee View Task List
| 7 | View Task Details | Feature | 2023-03-13 | 2023-04-02 | 18 | Planned |  | Employee View Task Details
| 7 | Search Project | Feature | 2023-03-13 | 2023-04-02 | 18 | Planned |  | Employee Search Project
| 7 | View Project List | Feature | 2023-03-13 | 2023-04-02 | 18 | Planned |  | Employee View Project List
| 7 | Update Task | Feature | 2023-03-13 | 2023-04-02 | 18 | Planned |  | Employee Update Task
| 7 | View Payroll | Feature | 2023-03-13 | 2023-04-02 | 18 | Planned |  | Employee View Payroll
| 7 | View Payroll Details | Feature | 2023-03-13 | 2023-04-02 | 18 | Planned |  | Employee View Payroll Details
| 7 | Search Payroll | Feature | 2023-03-13 | 2023-04-02 | 18 | Planned |  | Employee Search Payroll